## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  |  |  | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project setup and environment configuration (Python, VS Code, Libraries Installation) | MUST HAVE | Python, VS Code | Anshu | 3- Completed
S1 | S1 | US-002 | Dataset collection and cleaning (orders.csv preprocessing) | MUST HAVE | Pandas | Anshu | 3- Completed
S2 | S2 | US-003 | Create embeddings using Sentence Transformers | MUST HAVE | sentence-transformers | Anshu | 3- Completed
S2 | S2 | US-004 | Build FAISS index for similarity search | MUST HAVE | FAISS | Anshu | 3- Completed
S3 | S3 | US-005 | Implement Retrieval-Augmented Generation (RAG) pipeline | MUST HAVE | LangChain | Anshu | 3- Completed
S3 | S3 | US-006 | Store structured data in Neo4j Knowledge Graph | SHOULD HAVE | Neo4j | Anshu | 3- Completed
S4 | S4 | US-007 | Connect RAG pipeline with Knowledge Graph | SHOULD HAVE | Neo4j + LangChain | Anshu | 3- Completed
S4 | S4 | US-008 | Develop Streamlit User Interface for query input | MUST HAVE | Streamlit | Anshu | 3- Completed
S5 | S5 | US-009 | Add visualization dashboard (charts, graphs, network visualization) | SHOULD HAVE | Plotly, PyVis | Anshu | 3- Completed
S6 | S6 | US-010 | Implement multilingual support (multiple languages query support) | COULD HAVE | Language APIs | Anshu | 3- Completed
S7 | S7 | US-011 | Testing and debugging of the full system | MUST HAVE | Unit Testing | Anshu | 2- In Progress
S8 | S8 | US-012 | Deployment of application (Render/Cloud) | MUST HAVE | Render | Anshu | 2- In Progress

## Sprint Backlog1Project Setup +
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 15 | 3 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG : Project Setup + Workflow Planning
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | T-001 | Install Python and required libraries | 2026-03-01 | 2026-03-02 | Anshu | Setup | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Create project workflow diagram | 2026-03-02 | 2026-03-03 | Sahana | Planning | Completed | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-003 | Define project modules and goals | 2026-03-03 | 2026-03-04 | Anshu | Documentation | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog5
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 14 | 4 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG:RAG Pipeline Development
US-005 | T-008 | Implement RAG retrieval pipeline | 2026-03-12 | 2026-03-13 | Anshu | Backend Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-009 | Integrate FAISS search with query system | 2026-03-13 | 2026-03-14 | Sahana | Integration | Completed | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog 6
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 13 | 3 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG : Neo4j Knowledge Graph
US-006 | T-010 | Install and configure Neo4j database | 2026-03-15 | 2026-03-16 | Anshu | Database Setup | In Progress | 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-011 | Create nodes and relationships in Neo4j | 2026-03-16 | 2026-03-17 | Sahana | Knowledge Graph | In Progress | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog 7
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 14 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG:Streamlit UI + Testing
US-007 | T-012 | Develop Streamlit interface | 2026-03-18 | 2026-03-19 | Anshu | UI Development | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-013 | Perform system testing | 2026-03-19 | 2026-03-20 | Sahana | Testing | Planned | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog 8
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG : Deployment
US-008 | T-014 | Deploy application on Render | 2026-03-21 | 2026-03-22 | Anshu | Deployment | Planned | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-015 | Final validation and testing | 2026-03-22 | 2026-03-23 | Sahana | Validation | Planned | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog 4
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG:FAISS Index
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-004 | T-007 | Create FAISS index | 2026-03-10 | 2026-03-11 | Anshu | Indexing | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog2
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 11 | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG : Dataset Work
US-002 | T-004 | Load dataset using Pandas | 2026-03-05 | 2026-03-06 | Anshu | Data Processing | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-005 | Clean dataset and handle missing values | 2026-03-06 | 2026-03-07 | Sahana | Data Cleaning | Completed | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog3
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG :Embeddings
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-003 | T-006 | Generate embeddings using model | 2026-03-08 | 2026-03-09 | Anshu,Sahana | ML Processing | Completed | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Python installation error | Reinstalled Python and verified PATH
Sprint 1 | Day 2 | Library compatibility issue | Installed correct versions using pip
Sprint 2 | Day 1 | Dataset loading error | Checked file path and corrected location
Sprint 2 | Day 2 | Missing values confusion | Used pandas methods to clean dataset
Sprint 3 | Day 1 | Model loading slow | Optimized model loading settings
Sprint 3 | Day 2 | Embedding generation delay | Reduced batch size for faster processing
Sprint 4 | Day 1 | FAISS installation error | Reinstalled FAISS with compatible version
Sprint 4 | Day 2 | Index creation failure | Verified embedding dimensions
Sprint 5 | Day 1 | Retrieval mismatch issue | Adjusted search parameters
Sprint 5 | Day 2 | Response formatting issue | Updated response generation logic
Sprint 6 | Day 1 | Neo4j connection error | Checked database credentials
Sprint 6 | Day 2 | Graph creation confusion | Reviewed Neo4j documentation
Sprint 7 | Day 1 | UI alignment problem | Modified layout in Streamlit
Sprint 7 | Day 2 | Button response delay | Optimized backend calls
Sprint 8 | Day 1 | Deployment environment error | Updated dependency versions
Sprint 8 | Day 2 | Final testing mismatch | Fixed minor bugs and retested

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-01 | 2026-03-04 | Anshu | Better environment setup planning | Avoid skipping installation checks | Follow documentation carefully | Created setup checklist
2 | Sprint 1 | 2026-03-01 | 2026-03-04 | Sahana | Communicate setup progress | Avoid duplicate installations | Verify software versions | Maintained shared setup notes
3 | Sprint 2 | 2026-03-05 | 2026-03-07 | Anshu | Perform data validation early | Avoid ignoring missing data | Maintain dataset backups | Implemented data cleaning steps
4 | Sprint 2 | 2026-03-05 | 2026-03-07 | Sahana | Test dataset loading regularly | Avoid incorrect file paths | Use version control for data | Organized dataset folders
5 | Sprint 3 | 2026-03-08 | 2026-03-09 | Anshu | Monitor embedding performance | Avoid large batch processing | Use efficient embedding methods | Optimized embedding settings
6 | Sprint 3 | 2026-03-08 | 2026-03-09 | Sahana | Document embedding workflow | Avoid skipping logs | Continue performance checks | Maintained execution logs
7 | Sprint 4 | 2026-03-10 | 2026-03-11 | Anshu | Validate FAISS outputs | Avoid incorrect index mapping | Continue testing search accuracy | Verified index configuration
8 | Sprint 4 | 2026-03-10 | 2026-03-11 | Sahana | Check indexing parameters | Avoid dimension mismatch | Continue logging operations | Fixed configuration settings
9 | Sprint 5 | 2026-03-12 | 2026-03-14 | Anshu | Improve query handling | Avoid incomplete responses | Continue testing retrieval logic | Updated retrieval functions
10 | Sprint 5 | 2026-03-12 | 2026-03-14 | Sahana | Validate response accuracy | Avoid skipping test queries | Continue debugging | Improved integration testing
11 | Sprint 6 | 2026-03-15 | 2026-03-17 | Anshu | Optimize Neo4j queries | Avoid inefficient queries | Continue monitoring database | Updated query structure
12 | Sprint 6 | 2026-03-15 | 2026-03-17 | Sahana | Maintain database logs | Avoid incorrect relationships | Continue graph validation | Fixed relationship mapping
13 | Sprint 7 | 2026-03-18 | 2026-03-20 | Anshu | Improve UI responsiveness | Avoid cluttered layouts | Continue usability testing | Updated Streamlit layout
14 | Sprint 7 | 2026-03-18 | 2026-03-20 | Sahana | Improve UI design clarity | Avoid slow loading components | Continue UI testing | Optimized UI elements
15 | Sprint 8 | 2026-03-21 | 2026-03-23 | Anshu | Monitor deployment logs | Avoid skipping final tests | Continue validation checks | Performed final testing
16 | Sprint 8 | 2026-03-21 | 2026-03-23 | Sahana | Validate deployment steps | Avoid missing dependencies | Continue documentation | Created deployment guide